## Sheet1
York College Capital Projects 2026 QTR 2 Update
Projects Ongoing- Being Built/ Filed |  | Status
Academic Core Building (ACB)
1 | ACB Toilets ADA Upgrade | Phase 1 completed in June 2026, approximately 50% completion | 17000000
2 | Fire Alarm Upgrade | Project just started; below 5% completion (JOCs) | 10000000
3 | Emergency- ACB main Gas line leak repair | Worked performed via JOCs contract: 100% Complete | N/A
4 | Sub-Basement groundwater grouting | Project just started; below 5% completion | 500000
5 | ACB Water Dist. Sys Study | Project just started; below 5% completion | 2900000
Performing Arts Center (PAC)
6 | Interior & HVAC Upgrades | Overall at 65% completion | 40000000
7 | Fire Alarm Upgrade | Project kickoff occurred; below 5% completion (JOCs) | 3800000
8 | Facade Leaks | Pending | 200000
Science Building (SB)
9 | Certificate of Occupancy (C of O) | Completion after HVAC-Roof Replacement Project/ TCO will be in place pending completion of above work | 250000
Campus
10 | 159th Street DRI Walkway Upgrade | Scope includes new paving, seating, lighting and access gate, 65% completed | 1000000
Sub-Total |  |  | 75650000
Project Pipeline- Being designed/ prepared for bidding
Classroom Bldg.
11 | Classroom Bldg. New Roof | Bid preperation- 2027 QTR 1 Construction Start | 6000000
12 | Window Replacement and Façade Restoration, interior upgrades | Bid preperation- 2027 QTR 1 Construction Start | 3000000
13 | MEP Upgrades | Bid preperation- 2027 QTR 1 Construction Start | 10700000
Science Building
14 | RTU & Roof Replacement | Bid preperation- 2027 QTR 1 Construction Start | 10000000
15 | Window Replacement & Interior upgrades | Bid preperation- 2027 QTR 1 Construction Start | 3000000
Track and Field
16 | New Indoor Tennis Complex w/ covering | Procurement of design services | 15000000
17 | Field House upgrades, and subsurface drainage improvements | Procurement of design services | 11500000
Campus wide
18 | Perimeter Fencing & Exterior lighting | Bid preperation- 2026 QTR 4 Construction Start | 8800000
19 | Automatic Gates | Design Development | 1500000
Sub-Total |  |  | 69500000
On the Horizon- Pre-Design
Campus Wide
20 | Updated Campus Master Plan | Procurement of design services | 1500000
Academic Core Building
21 | Pre- Design: Exterior Façade & Windows | Design Development | 16500000
22 | Laboratory Fume Hood Replacement | Scope reconsideration | 8100000
Sub-Total |  |  | 26100000
Grand Total |  |  | 171250000